## Project plan
Project plan
1- | choosing the robot we'll be working on
2- | decieding which engineers/ specialist the project needs
3- | gathering team members
4- | distruibuting and assigning tasks
5- | designing an apropriate timeline for each department
6- | start excution and follow up

## distribution of tasks
| task discription | Department | Assigned to | complete
1 | constructing 3d model | mechanical engineering | Amjad | 40%
2 | designing a new end effector | mechanical engineering | Reem and shoaa | 25%
3 | designing a electronic circuit | power and electronics | Hanan | 100%
to control 5 servers
4 | programming the circuit(rheostat) | power and electronics | Hanan | 20%
5 | designing the control panel | IOT | Abeer | 90%
6 | creating a database for the control panel | IOT | Hanan | 40%
8 | linking the database with control panel | IOT | Abeer | 0%
9 | installing arm package on ROS | AI | Shaden and leen | 80%
10 | linking ROS to control panel | AI | Alhanouf and dana | 0%

## Timeline
Timeline of project
| week1 | week2 | week3 | week4 | week5 | week6 | week7 | week8
mechanical design | bar: week1 to Timeline of project week2
power and electronics | bar: Timeline of project week2 to Timeline of project week4
programming and AI | bar: Timeline of project week4 to Timeline of project week5
IOT | bar: Timeline of project week6 to Timeline of project week7
Assembly | bar: Timeline of project week8

## Production line
Production line
Modelling
Assembly
Packaging
Application